## Man days
No | Module / Task | Detail | Design (days) | FE (days) | Backend (days) | Note
| Planning |  |  |  | 1 | Env setup, Discord bot + Railway config, Notion API & MCP tokens, YAML skeleton
1 | Discord Gateway
|  | Bot Auth & Connection + Channel Allow/Deny Filter | 0 | 0 | 1
|  | @Mention Listener + Rate Limiter + Response Formatter (Embeds) + Error Messenger | 0 | 0 | 1
2 | Query Parser
|  | Session Manager (in-memory, 30min timeout, history injector, reset command) | 0 | 0 | 1
|  | Intent Classifier (8 intents) + Language Detector (ID / EN) | 0 | 0 | 1
|  | Entity Extractor + Fuzzy Matcher + Ambiguity Handler | 0 | 0 | 1
|  | Multi-Question Splitter + cross-question entity inheritance | 0 | 0 | 1
3 | Notion Data Router
|  | Route Decision Engine + Workspace DB Registry (YAML config) | 0 | 0 | 1
|  | Property Name Normalizer + Multi-hop Coordinator + Null Fallback | 0 | 0 | 1
4 | Data Fetcher
|  | Notion API Client: project search, property fetch, bug count, changelog | 0 | 0 | 2
|  | Notion MCP Client: workspace search, page nav, content reader, credential extractor | 0 | 0 | 1
|  | Cache Layer: per-tier TTLs (30min / 5min / 15min / no-cache for credentials) | 0 | 0 | 1
5 | LLM Response Synthesizer
|  | Prompt Builder + Multi-answer Formatter + Language Instruction | 0 | 0 | 1
|  | Hallucination Guardrail + Credential Formatter + Not-Found Handler + Cost Guard | 0 | 0 | 1
6 | Config & Observability
|  | YAML Config (channel, DB registry, LLM, cache TTLs) + FastAPI Health Check endpoint | 0 | 0 | 0.5
|  | Latency Logger + Error Tracker + Query Audit Log | 0 | 0 | 0.5
Integration & Testing
|  | End-to-end integration across all 6 modules + internal testing + bug fixes | 0 | 0 | 2
UAT + Deployment
|  | UAT (PM, Dev, QA, CS, Sales) + revision + Railway prod deploy + post-launch monitoring | 0 | 0 | 2
TOTAL
Total Mandays
|  | Base Cost (IDR / manday) | 500000
Total Development Cost
|  | PM Cost (1 month × IDR 2,000,000) | 2000000
|  | Tester Cost (2 review days × IDR 200,000) | 400000
Grand Total
Yearly Maintenance (10% × Grand Total)
Monthly Maintenance
Extra Cost — One-time project (30% × Grand Total)

## Simple Gantt
No | Stage | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Planning & Setup | bar: Week 1 1
2 | Module 1 — Discord Gateway | bar: Week 1 2 to Week 1 3
3 | Module 2 — Query Parser | bar: Week 1 4 to Week 2 3
4 | Module 3 — Notion Data Router | bar: Week 2 4 to Week 2 5
5 | Module 4 — Data Fetcher (API + MCP + Cache) | bar: Week 3 1 to Week 3 4
6 | Module 5 — LLM Response Synthesizer | bar: Week 3 5 to Week 4 1
7 | Module 6 — Config & Observability | bar: Week 4 2
8 | Integration & Testing | bar: Week 4 3 to Week 4 4
9 | UAT + Deployment | bar: Week 4 5

## Detail Timeline (in Week)
Timedoor Project Assistant Bot Project Plan | Task / Sub-task | PIC | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4
|  |  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Planning
| Env setup (Python 3.11, discord.py, FastAPI, LangChain) | Tmdr | bar: Week 1 1
| Discord bot registration + Railway project init + GitHub repo | Tmdr | bar: Week 1 1
| Notion API token + Notion MCP server setup | Tmdr | bar: Week 1 1
| YAML config skeleton + project folder structure | Tmdr | bar: Week 1 1
Development
| Module 1 — Discord Gateway | Tmdr | bar: Week 1 2 to Week 1 3
| └ Bot auth & connection + channel allow/deny filter | Tmdr | bar: Week 1 2
| └ @Mention listener + rate limiter + error messenger | Tmdr | bar: Week 1 2 to Week 1 3
| └ Response formatter (Discord Embeds, color-coded) | Tmdr | bar: Week 1 3
| Module 2 — Query Parser | Tmdr | bar: Week 1 4 to Week 2 3
| └ Session Manager (store, timeout, injector, reset cmd) | Tmdr | bar: Week 1 4
| └ Intent Classifier (8 intents) + Language Detector ID/EN | Tmdr | bar: Week 1 5
| └ Entity Extractor + Fuzzy Matcher + Ambiguity Handler | Tmdr | bar: Week 2 1 to Week 2 2
| └ Multi-Question Splitter + cross-Q entity inheritance | Tmdr | bar: Week 2 3
| Module 3 — Notion Data Router | Tmdr | bar: Week 2 4 to Week 2 5
| └ Route Decision Engine (Tier 1/2 → API, Tier 3 → MCP) | Tmdr | bar: Week 2 4
| └ Property Name Normalizer + Multi-hop Coordinator | Tmdr | bar: Week 2 5
| Module 4 — Data Fetcher | Tmdr | bar: Week 3 1 to Week 3 4
| └ Notion API Client (project search, property, bugs, changelog) | Tmdr | bar: Week 3 1 to Week 3 2
| └ Notion MCP Client (page nav, content reader, cred extractor) | Tmdr | bar: Week 3 3
| └ Cache Layer (30min / 5min / 15min / no-cache per tier) | Tmdr | bar: Week 3 4
| Module 5 — LLM Response Synthesizer | Tmdr | bar: Week 3 5 to Week 4 1
| └ Prompt Builder + Multi-answer Formatter + Language instr. | Tmdr | bar: Week 3 5
| └ Hallucination Guardrail + Credential Formatter | Tmdr | bar: Week 4 1
| Module 6 — Config & Observability | Tmdr | bar: Week 4 2
| └ YAML Config + DB Registry + LLM/cache config + Health Check | Tmdr | bar: Week 4 2
| └ Latency Logger + Error Tracker + Query Audit Log | Tmdr | bar: Week 4 2
Testing
| Integration testing across all 6 modules | Tmdr | bar: Week 4 3
| Internal QA: Tier 1/2 structured + Tier 3 MCP queries | Tmdr | bar: Week 4 3 to Week 4 4
| Bug fixes + edge case handling + latency verification | Tmdr | bar: Week 4 4
UAT & Launch
| User Acceptance Testing (PM, Dev, QA, CS, Sales roles) | Tmdr | bar: Week 4 5
| Revision based on UAT feedback | Tmdr | bar: Week 4 5
| Railway production deploy + post-launch monitoring | Tmdr | bar: Week 4 5
| Documentation handover | Tmdr | bar: Week 4 5

## Summary Gantt
No | Module / Phase | Days | Week 1 (D1–5) | Week 2 (D6–10) | Week 3 (D11–15) | Week 4 (D16–20) | Key Deliverables
— | Planning & Setup | 1 | ■ |  |  |  | Env ready, bot token, Notion token, Railway project, config skeleton
1 | Module 1 — Discord Gateway | 2 | ■ |  |  |  | Bot listening in Discord, channel filter live, rate limiter, embed formatter
2 | Module 2 — Query Parser | 4 | ■ | ■ |  |  | Session store, intent classifier, fuzzy matcher, multi-Q splitter
3 | Module 3 — Notion Data Router | 2 |  | ■ |  |  | Tier 1/2/3 routing, property normalizer, multi-hop coordinator
4 | Module 4 — Data Fetcher | 4 |  |  | ■ |  | Notion API client, MCP client, cache layer with per-tier TTLs
5 | Module 5 — LLM Response Synthesizer | 2 |  |  | ■ | ■ | Prompt builder, guardrails, credential formatter, bilingual output
6 | Module 6 — Config & Observability | 1 |  |  |  | ■ | YAML config, health check endpoint, latency/error/audit logging
— | Integration & Testing | 2 |  |  |  | ■ | End-to-end tests, internal QA across all query types, bug fixes
— | UAT + Deployment | 2 |  |  |  | ■ | UAT sign-off, Railway prod deploy, post-launch monitoring
| TOTAL | 20 |  |  |  |  | 20 working days ¦ 4 calendar weeks